## Features
JsonPretty
Feature | Status | Description
General
remembers user settings | y
wndow position | y
parses json | y
parses xml | y
monitors clipboard | y
Main Window | y
menu | y
file | y
quit | y
save as | n
edit | y
copy | y
copies plaintext | y
copies html with color | y
copies rtf with color | y
save selection as | n
html | n
rtf | n
plain text | n
select all | y
monitor clipboard checkbox | y
paste from clipboard | y
view | y
show tool bar | n
detail pane on side | y
help | y
about | n
toolbar | n
monitor clipboard checkbox | y
paste button | y
search box | n
content area | y
json syntax highlight | y
xml syntax highlight | y
handles invalid text | y
formats json | y
detail pane | y
monitors selection | y
parse | y
ip address | n
unicode int to char | n
unicode \uxxxx escape -> decimal, char | n
hex to utf8 | y
hex to ascii | y
java time | y
shows time zone | y
unix time | y
shows time zone | y
base64 | y
base64 utf8 | y
base64 ascii | y
hex color values | n
de-escape json string | n
status line | y
copyright | y
on click navigates to Help->About | n
memory monitor | n
History | n
keep last N entries | n
diff two entries | n
Options | n
syntax colors | n
name | n
string | n
value | n
error | n
xml tag | n
xml attribute | n
xml attribute value | n
text | n
comment | n
color themes | n
dark | n
light | n
format options | n
Check for Updates Dialog | n
checking | n
result | n
web site | n
License Dialog | n
license | n
Copy to Clipboard button | n
OK | n
About Dialog | n
logo | n
link | n
Features implemented: | 41
To be implemented: | 45
To be determined: | 0
Total: | 86
| Percent complete: | 47.67%

## Progress
JsonPretty
Date | Done | To Do | To Be Defined | Defects | Version | %
2017-10-03 | 0 | 0 | 0 | 0 | Start | 0%
3/19/17 | 8 | 55 | 0 | 0 | 0.00.01 | 12.7%
3/21/17 | 17 | 46 | 0 | 0 | 0.00.02 | 26.98%
3/29/17 | 25 | 42 | 0 | 0 | 0.00.03 | 37.31%
2017-02-04 | 27 | 42 | 0 | 0 | 0.00.04 | 39.13%
2017-12-04 | 29 | 38 | 0 | 0 | 0.00.05 | 43.28%
04-29-2017 | 31 | 40 | 0 | 0 | 0.00.06 | 43.66%
04-30-2017 | 31 | 40 | 0 | 0 | 0.00.07 | 43.66%
05-15-2017 | 35 | 40 | 0 | 0 | 0.00.08 | 46.67%
2017-03-06 | 36 | 42 | 0 | 0 | 0.00.09 | 46.15%
2017-03-06 | 39 | 40 | 0 | 4 | 0.00.10 | 46.99%
2017-10-06 | 41 | 45 | 0 | 2 | 0.00.11 | 46.59%
Total | Done | To Do | To Be Defined | Defects | Version | 46.59%
86 | 41 | 45 | 0 | 2
2017-10-03